## Sheet1
Weeks
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Study of AOM and inherent patterns
Study of the Oghma framework
Mining of Web Patterns for AOMs
Implementation
Tests
Dissertation writing
| September 13 | [19 empty] | January 31